## Slide 1: 2016-2017 Steel Bridge Team
CENE 486C
April 28, 2017
Sabrina Ballard
Sean Hopper
Ryan Morofsky
Meg Stevens

## Slide 2: Project Description
Project Purpose
  American Institute of Steel Construction (AISC) and American Society of Civil Engineers (ASCE) Student Steel Bridge Competition
  1:10 scale model steel bridge
Technical Considerations
  50 pounds lateral load
  2500 pounds vertical load
Potential Challenges
  Member sizes under 36”x4”x6”
  Minimizing deflection and weight
2 Morofsky
Figure 1. Official Rules [1]

## Slide 3: Project Understanding
Client
Technical Advisor
Stakeholders
  Future owners of homes in Beaver Lodge Estates
  Northern Arizona University (NAU) ASCE Student Chapter
Mark Lamer, PE
Thomas Nelson, MS, PE, SE
3 Morofsky

## Slide 4: Identification of Alternatives
Footings
  AB vs AC
Bridge Types
  Top chord vs beam bridge
Connections
  Gusset plate vs slip connection
4 Morofsky
Figure 2. Footing Options

## Slide 5: Identification of Selected Designs
Bridge Members
 |  | 4x6 HSS Tubing | 2D Mini-Truss | Triangular 3D Mini-Truss | Square 3D Mini-Truss | Rectangular 3D Mini-Truss
 | Weight % | Weighted Score | Weighted Score | Weighted Score | Weighted Score | Weighted Score
Deflection | 75% | 0.75 | 1.5 | 3 | 2.25 | 3.75
Weight | 25% | 1.25 | 1 | 0.75 | 0.5 | 0.25
Total | 100% | 2 | 2.5 | 3.75 | 2.75 | 4
5 Morofsky
Table 1: Bridge Member Decision Matrix

## Slide 6: Identification of Selected Designs
Defection Reduction
 |  | Increase Moment of Inertia | Increase Member Size | Increase Member Thickness
 | Weight % | Weighted Score | Weighted Score | Weighted Score
Deflection | 50% | 4.5 | 1.5 | 4.5
Weight | 50% | 4.5 | 0.5 | 0.5
Total | 100% | 9 | 2 | 5
6 Morofsky
Table 2: Deflection Reduction Decision Matrix

## Slide 7: Design Analysis - RISA Model
7 Ballard
Figure 3. RISA Load Combination 1-1
Figure 4. RISA Load Combination 1-2
-390 lb/ft
-390 lb/ft
-130 lb/ft

## Slide 8: Load Case 1-1 Deflection
8 Ballard

## Slide 9: Load Case 1-2 Deflection
9 Ballard

## Slide 10: Final Design
10 Ballard
Figure 5. Final RISA Design
Mini Truss 1/4” rod
1”x1”x1/16” HSS bottom chord
3/4”x3/4”x1/16” HSS or 1/2”x1/2”x1/16” HSS top chord
1”x1/2”x1/16” HSS decking
Lateral Bracing
1/2”x1/2”x1/16” HSS.
Foundation Legs
3/4”x 3/4”x1/16” HSS
Substructure 1” x 1” x 1/16” HSS
3/4”x 3/4”x1/16” HSS
Substructure
Lateral Bracing
Foundation Legs
Mini-truss

## Slide 11: Connection Design
11 Ballard
Figure 7. Male Connection
Minimum Edge Distance
Bolt Shear Strength
Bolt Tensile Strength
Block Shear
Bearing Capacity
Tensile Yielding
Plate Bending Capacity
Figure 6. Female Connection

## Slide 12: Connection Design
\
12 Hopper
Figure 8. Solid Works Model
Figure 9. Substructure Connection

## Slide 13: Fabrication
Measured, cut, welded, grinded
Bent rod instead of cut
Welded on the nuts
Sandblasted and spray painted
13 Hopper
Figure 11. Completed Mini-Truss
Figure 10. Bending Rod in Jig

## Slide 14: Pacific Southwest Conference
14 Hopper
Figure 12. Display Day
Figure 13. Timed Construction
Figure 14. Vertical and Lateral Load Test

## Slide 15: Pacific Southwest Conference
15 Hopper
Figure 15. Timed Construction Layout [1]

## Slide 16: Pacific Southwest Conference
16 Hopper
Figure 16. Completed Bridge After Construction

## Slide 17: Deflection Results
17 Stevens
 | Allowable Deflection (in) | Anticipated Deflection (in) | Actual Deflection (in)
Vertical | 3 | 0.645 | 2.3
Sway | 1 | 0.669 | PASS
Lateral | 0.5 | 0.252 | PASS
Figure 17. Bridge at Full Mid-Span Loading
Table 3. Deflections

## Slide 18: Conference Results
Construction Speed = 17:14 (4th place)
Weight = 243 lb (8th place)
Display = 3rd place
Aggregate Deflection = 4.41 inches (12th place)
Economy = $7,746,667 (6th place)
Efficiency = $16,840,000 (12th place)
Overall = $24,586,667 (9th place)
18 Stevens
Figure 18. Bridge and Team After Loading

## Slide 19: Project Schedule
Original Gantt Chart
19 Stevens
Figure 19. Original Gantt Chart

## Slide 20: Project Schedule
Final Gantt Chart
20 Stevens
Figure 20. Final Gantt Chart

## Slide 21: Summary of Project Costs
Estimated Cost vs Actual Cost
21 Stevens
$39,301 over estimated budget
1020 estimated hours
1734 actual hours
Total Cost of Services |  |  |  |  | 
Service | Rate | Est. Unit | Actual Unit | Est. Total Cost | Actual Total Cost
Personnel |  |  |  |  | 
PM | $117 per hour | 135 hours | 166 hours | $ 15,755 | $ 19,422
DSNENG | $78 per hour | 270 hours | 270 hours | $ 21,060 | $ 21,060
DRF | $54 per hour | 175 hours | 175 hours | $ 9,406 | $ 9,406
FAB | $45 per hour | 220 hours | 933 hours | $ 9,900 | $ 41,985
INT | $17 per hour | 220 hours | 220 hours | $ 3,751 | $ 3,740
Transportaiton |  |  |  |  | 
Lodging | 4 nights, 2 rooms | $140/night | $210/night | $ 1,120 | $ 1,680
Car Rental | 5 days | $150/day | $150/day | $ 750 | $ 750
Testing | $100 per hour | 20 hours | 20 hours | $ 2,000 | $ 2,000
Materials | Lump Sum | $4,000 | $7,000 | $ 4,000 | $ 7,000
Total |  |  |  | $ 67,742 | $ 107,043
Table 4. Cost of Services

## Slide 22: Impacts / Takeaways
Takeaways
  Equipment and Space Limitiations
    TIG welder
    Welding indoors
  Importance of connections
  Pre-testing the bridge
    Find areas of concern
22 Stevens
Impacts for future
  Communication
  Teamwork
  Project Management
Figure 21. Bridge Selfie

## Slide 23: References
[1] "ASCE - AISC Student Steel Bridge Competitions", Aisc.org, 2016. [Online]. Available: http://www.aisc.org/content.aspx?id=780.
[2] Excel. Microsoft, 2017.
[3] RISA-3D. RISA Technologies, 2017.
[4] Solidworks. Dassault Systemes, 2017.
[5] Project. Microsoft, 2017.
[6] American Institute of Steel Construction. Steel Construction Manual, 14th Ed., Fourth Printing

## Slide 24: Supplemental Information – Scoring Equations
For a bridge that weighs 303 pounds or less:
For a bridge that weighs more than 303 pounds:
Structural Efficiency, Cs [1]
Construction Economy, Cc [1]
Overall Score = Structural Efficiency + Construction Economy
Cs
Cs
Cc