## Slide 1: 67% Hardware Update
Boeing Autonomous
Elise C., Selina C., Jake K., Marek L., Desirae M., Natasa P., Lily Q.

## Slide 2: Design Efforts
Main Assembly of Go-Kart

## Slide 3: Brakes
ML 3
Brake Assembly

## Slide 4: Brakes
Updates
Motor Base Plate Completed
Keyed Caliper Arm Completed
Caliper Bracket Remanufacturing Complete
Systems 1st Test Complete
Calculations Changed
New Question: Does the new direct-drive ramp design generate sufficient clamping force to meet the 1015 N braking requirement?
Variables: τ_max=35Nm L_eff=0.00763m θ=60° η= 0.92
t_(60°,18v)=.16s v_1=18v v_2=24v
Equations:
Tangential Servo Force- F_tan= τ_max/L_eff [1,2]
Total Clamping Force= F_total= 2(F_tan*tanθη) [1,3,5]
Brake Actuation Time- t_120°=2(t_(60°,18v)(v_1/v_2)) [4]
Conclusion: The direct-drive design with the Docyke 350 kg·cm servo keyed into the modified 60° ramped lever arm (L_eff = 7.63 mm) produces 14,628 N total clamping force (14.4× the required 1,015 N) and completes 120° full-brake actuation in 72 ms (FoS_time = 2.08).
JK 4

## Slide 5: Brakes
ML 5
Modified Lever Arm
Base Plate
Brake Caliper

## Slide 6: Steering
SC 6
Updates:
Motor Mount Completion
EE motor tests
Mechanical Failsafe Design Completion
100% Purchasing Completed
100% Design Completed
Calculations:
Linear Actuator Pull Verification
Linear Actuator Baseplate thickness
Technical Drawing of Completed Steering Assembly

## Slide 7: Steering
SC 7
Calculation Design Results
Required linear actuator push/pull: 22.8N (FOS of 2)
Baseplate thickness is negligible (~0.6mm minimum) for pulling/pushing the motor mount
  Conclusion: Will proceed with ~3.5mm thickness to account for additional factors such as vibration, screw deformation, and weight of linear actuator
*All calculations can be found in the appendix

## Slide 8: Steering
Motor Mount Subassembly
SC 8

## Slide 9: Steering
Previous Baseplate Drawing
Previous Top Plate Drawing
Previous Wedge Drawing
Motor Mount Pieces Before
SC 9

## Slide 10: Steering
Baseplate Drawing
Top Plate Drawing
Wedge Drawing
Motor Mount Pieces Final Dimensions
SC 10

## Slide 11: Steering
Linear Actuator Subassembly
SC 11

## Slide 12: Steering
Linear Actuator Pieces (Failsafe)
SC 12
Linear Actuator Baseplate Drawing
Linear Actuator Mount Wedge Drawing

## Slide 13: Steering
Gearbox Progression
SC 13
Previous Gear Box Design
Current Gear Box Design

## Slide 14: Steering
Previous Gearbox Front
Previous Gearbox Back
Previous Gearbox Drawings
SC 14

## Slide 15: Steering
Current Gearbox Front
Current Gearbox Back
Current Gearbox Drawings
SC 15

## Slide 16: Throttle
NP 16
Design Overview
Changes:
Cable
  New Bowden Cable
Assembly Location
  Bottom Chassis
Spool
  Re-designed with (2) Set Screws and End Mount for Encoder
Stepper Mount
  (1) Welded 3 x 3in. L-Bracket
Mechanical Driving System
  Electric Pedal
Throttle Springs
  Updated with More Resistance
Final Throttle Stepper Assembly
Final Electrical Pedal Assembly

## Slide 17: Throttle
Design Evolution
NP 17
Previous Stepper Design
Updated Stepper Design
Previous Acceleration Control Design
Updated Pedal Control Design
Original Bowden Support
Updated Bowden Support

## Slide 18: Throttle
Schematics
NP 18
Final Throttle Stepper Assembly
Throttle Stepper Spool

## Slide 19: Throttle
Schematics
Bowden Cable Mounting Plate
L-Bracket for Encoder
NP 19

## Slide 20: Purchasing & Manufacturing Plan

## Slide 21: Brakes
JK 21
Completed ​
All Manufacturing
In Progress​
Fine Tuning and System Testing with EE's
Scheduled​
Chamfer Base Plate Edges and Cut Screws to Size (Feb 25th)
Bore Larger Hole in Caliper Body and System Testing Friday(Feb 26th)
System Testing Wednesday (March 4th)
% Purchased | 100 %
% On-Hand | 100 %
% Manufactured | 100%

## Slide 22: Steering
SC 22
% Purchased | 100%
% On-Hand | 100%
% Manufactured | 91.18%
Completed ​
Motor Mount
Mechanical Failsafe Design
Gearbox Design
In Progress​
Manufacturing linear actuator mount
Manufacturing gearbox
EE Motor Testing
Scheduled​
Finishing Linear Actuator Mount (2/27)
Assembling Linear Actuator Mount (3/2)
EE Mechanical Failsafe Testing (3/6)
Finalize all mechanical portions (3/16)
EE completed tests (4/16)

## Slide 23: Throttle
EC 23
Completed
Base plate
Pedal Mounted
In Progress
CNC Stepper Spool
Scheduled
Stepper Enclosure
Bowden Cable Mount Near Lever
EE Testing
  Electric Pedal
  Driver Issues
% Purchased | 100%
% On-Hand | 100%
% Manufactured | 67.89%

## Slide 24: Electrical
LQ 24
% Purchased | 92%
% On-Hand | 88.89%
% Manufactured | 24%
Completed
CAD Design of LiDAR camera ,Mount
In Progress
Mount for 24v Battery
Wiring & soldering
Emergency Stop Button
Scheduled
Hall Sensor Mounts
Mount for Electrical Box

## Slide 25: Budget
EC 25

## Slide 26: Demonstrations

## Slide 27: Brakes Demo
ML 27

## Slide 28: Steering
DM 28

## Slide 29: Steering
DM 29

## Slide 30: Throttle Demo
NP 30
Final Stepper Mount
Electric Pedal Mount
Updated Throttle Lever Spring

## Slide 31: Throttle Demo
NP 31

## Slide 32: Electrical Mounts
LiDAR Mount
LiDAR Sensor
weld
Previous LiDAR Mount
New LiDAR Mount
LQ 32

## Slide 33: Gantt Charts

## Slide 34: Brakes
 |  |  |  |  |  |  | 12-Jan | 19-Jan | 26-Jan | 2-Feb | 9-Feb | 16-Feb | 23-Feb | 2-Mar | 9-Mar | 16-Mar | 23-Mar | 30-Mar | 6-Apr | 13-Apr | 20-Apr | 27-Apr
Task | Project Lead/s | Start Date | End Date | Days | Estimated Hours | Actual Hours | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
Manufacturing 33% | Jacob, Marek | 1/24/26 | 2/3/26 | 10 | 7.5 | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Manufacturing 66% | Jacob, Marek | 2/3/26 | 2/13/26 | 10 | 15 | 66.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CAD Rework | Marek | 2/3/26 | 2/22/26 | 19 | 6 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Update Calculations | Jacob, Marek | 2/8/26 | 2/22/26 | 14 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First Test | Evan, Jacob, Marek | 2/19/26 | 2/20/26 | 1 | 4 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Second Test | Evan, Jacob, Marek | 2/26/26 | 2/27/26 | 1 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Design Optimiziation | Jacob, Marek | 2/14/26 | 2/28/26 | 14 | 15 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Electronics Configured | EE's, Jacob, and Marek | 2/10/26 | 2/20/26 | 10 | 2.5 | 2* |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Case Manufacuring | Jacob, Marek | 2/26/26 | 3/3/26 | 5 | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Third Test | Jacob, Marek | 3/1/2026 | 3/7/26 | 6 | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Remanufacturing | Jacob, Marek | 3/1/2026 | 3/9/2026 | 8 | 40 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Final Testing | Jacob, Marek | 3/16/2026 | 3/27/2026 | 11 | 25 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ML 33

## Slide 35: Steering
LQ 34
 |  |  |  |  |  | Week |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task | Start Date | End Date | Days | Estimated Hours | Actual Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Final CAD | 12-Jan | 20-Jan | 8 | 15 | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Motor Testing | 20-Jan | 30-Jan | 10 | 8 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Gearbox Manufacturing | 20-Jan | 2-Feb | 13 | 4 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Gear Mounting | 20-Jan | 2-Feb | 13 | 2 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Motor Mount Manufacturing | 20-Jan | 15-Feb | 26 | 10 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Motor and Gearbox Mounting | 15-Feb | 22-Feb | 7 | 6 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing Gears with Motor | 15-Feb | 1-Mar | 14 | 2 | 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Failsafe Mount Manufacturing | 17-Feb | 27-Feb | 10 | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Failsafe Mounting | 25-Feb | 2-Mar | 4 | 2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Initial Testing with Entire System | 1-Mar | 15-Mar | 14 | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Finalizations | 16-Mar | 30-Mar | 14 | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 36: Throttle
 |  |  |  |  |  | Week |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Throttle Subsystem | Start Date | End Date | Days | Estimated Hours | Actual Hours | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Project Summary and Management | 12-Jan | 19-Jan | 7 | 15 | 18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Redesign of Stepper Mount | 20-Jan | 24-Jan | 4 | 8 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mounting Stepper Mechanism | 25-Jan | 29-Jan | 5 | 12 | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing Stepper Mechanism (33% Progress) | 30-Jan | 01-Feb | 3 | 6 | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Designing Mount for Electric Pedal | 04-Feb | 10-Feb | 6 | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Test Electric Pedal | 12-Feb | 14-Feb | 3 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve Spring Strength in Throttle Lever | 15-Feb | 20-Feb | 5 | 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Improve Base Plate for Stepper (67% Progress) | 21-Feb | 24-Feb | 3 | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Re-Manufacture Spool using Metal | 25-Feb | 04-Mar | 7 | 15 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing and Improving all Components | 16-Mar | 27-Mar | 14 | 30 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
NP 35

## Slide 37: Thank you!
Questions?

## Slide 38: References
[1] E. Oberg and C. J. Mccauley, Machinery’s handbook : a reference book for the mechanical engineer, designer, manufacturing engineer, draftsman, toolmaker, and machinist. New York: Industrial Press, 2012.
[2] J. H. Jung, N. Pan, and T. J. Kang, “Capstan equation including bending rigidity and non-linear frictional behavior,” Mechanism and Machine Theory, vol. 43, no. 6, pp. 661–675, Jun. 2008, doi: https://doi.org/10.1016/j.mechmachtheory.2007.06.002.
‌
[3] R. G. Budynas, J Keith Nisbett, and Joseph Edward Shigley, Shigley’s mechanical engineering design, 11th ed. New York, Ny: Mcgraw-Hill Education, 2020.
[1] R. C. Hibbeler, Engineering Mechanics: Statics, 14th ed. Upper Saddle River, NJ, USA: Pearson, 2016.
[2] F. P. Beer, E. R. Johnston Jr., J. T. DeWolf, and D. F. Mazurek, Vector Mechanics for Engineers: Statics and Dynamics, 11th ed. New York, NY, USA: McGraw-Hill Education, 2016.
[3] R. L. Norton, Machine Design: An Integrated Approach, 6th ed. Boston, MA, USA: Pearson, 2019.
[4] S. J. Chapman, Electric Machinery Fundamentals, 5th ed. New York, NY, USA: McGraw-Hill Education, 2012.
[5] T. D. Gillespie, Fundamentals of Vehicle Dynamics, Warrendale, PA, USA: SAE International, 1992.
‌

## Slide 39: Appendix- Brakes
Sufficient Clamping Force Verification

## Slide 40: Appendix - Steering
Linear Actuator Push/Pull Verification
Minimum Thickness for Linear Actuator Plate