## Sheet1
Project Title: Lagamorph Plus
Team Members:
Kiwi | Chewie | Taffy | Chauncey | <Name> | <Name>
[5 empty] | Start Week: | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15
Team Member(s) absent from weekly Mentor Meeting:
[5 empty] | Task Description: | 2023-01-16: Project preference memo; 2023-01-23: Create team name; 2023-02-06: Team standards doc - introduction
[5 empty] | Assigned Team Member(s): | 2023-01-16: Kiwi; 2023-01-23: All; 2023-02-06: Kiwi
[5 empty] | Start Date: | 2023-01-16: 2022-01-27; 2023-01-23: 2022-02-06; 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-01-16: 2022-02-01; 2023-01-23: 2022-02-10; 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-01-16: includes all items specified in given instructions; 2023-01-23: All specified actions are completed; 2023-02-06: grammatically correct, introduction as specified
[5 empty] | Actual Outcome: | 2023-01-16: met requirements; 2023-01-23: met requirements; 2023-02-06: pending
[5 empty] | Current Status: | 2023-01-16: completed; 2023-01-23: completed; 2023-02-06: pending
[5 empty] | Task Description: | 2023-01-16: Project preference memo; 2023-02-06: team standards doc - team members, roles
[5 empty] | Assigned Team Member(s): | 2023-01-16: Chewie; 2023-02-06: Chewie
[5 empty] | Start Date: | 2023-01-16: 2022-01-27; 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-01-16: 2022-02-01; 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-01-16: includes all items specified in given instructions; 2023-02-06: grammatically correct, team standards component, as specified
[5 empty] | Actual Outcome: | 2023-01-16: forgot to put picture in memo; 2023-02-06: pending
[5 empty] | Current Status: | 2023-01-16: completed; 2023-02-06: pending
[5 empty] | Task Description: | 2023-01-16: Project preference memo; 2023-02-06: team standards doc - meeting requirements
[5 empty] | Assigned Team Member(s): | 2023-01-16: Taffy; 2023-02-06: Taffy
[5 empty] | Start Date: | 2023-01-16: 2022-01-27; 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-01-16: 2022-02-01; 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-01-16: includes all items specified in given instructions; 2023-02-06: grammatically correct, meeting requirements as specified
[5 empty] | Actual Outcome: | 2023-01-16: did not use memo format for document; 2023-02-06: pending
[5 empty] | Current Status: | 2023-01-16: completed; 2023-02-06: pending
[5 empty] | Task Description: | 2023-01-16: Project preference memo; 2023-02-06: team standards doc - tools and document standards
[5 empty] | Assigned Team Member(s): | 2023-01-16: Chauncey; 2023-02-06: Chauncey
[5 empty] | Start Date: | 2023-01-16: 2022-01-27; 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-01-16: 2022-02-01; 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-01-16: includes all items specified in given instructions; 2023-02-06: grammatically correct, tools, document standards as specified
[5 empty] | Actual Outcome: | 2023-01-16: met requirements; 2023-02-06: pending
[5 empty] | Current Status: | 2023-01-16: completed; 2023-02-06: pending
[5 empty] | Task Description: | 2023-02-06: team standards doc - completed document
[5 empty] | Assigned Team Member(s): | 2023-02-06: All team members
[5 empty] | Start Date: | 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-02-06: grammatically correct, fully reviewed by team, meets all requirements
[5 empty] | Actual Outcome: | 2023-02-06: pending
[5 empty] | Current Status: | 2023-02-06: pending
[5 empty] | Task Description: | 2023-02-06: Team inventory doc - cover page and introduction
[5 empty] | Assigned Team Member(s): | 2023-02-06: Taffy
[5 empty] | Start Date: | 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-02-06: grammatically correct, cover page and introduction as specified
[5 empty] | Actual Outcome: | 2023-02-06: pending
[5 empty] | Current Status: | 2023-02-06: pending
[5 empty] | Task Description: | 2023-02-06: Team inventory doc - cover page and introduction
[5 empty] | Assigned Team Member(s): | 2023-02-06: Taffy
[5 empty] | Start Date: | 2023-02-06: 2022-02-06
[5 empty] | End Date: | 2023-02-06: 2022-02-24
[5 empty] | Measureable Outcome: | 2023-02-06: grammatically correct, cover page and introduction as specified
[5 empty] | Actual Outcome: | 2023-02-06: pending
[5 empty] | Current Status: | 2023-02-06: pending
Task Description:
Assigned Team Member(s):
Start Date:
End Date:
Measureable Outcome:
Actual Outcome:
Current Status:
Task Description:
Assigned Team Member(s):
Start Date:
End Date:
Measureable Outcome:
Actual Outcome:
Current Status:
Task Description:
Assigned Team Member(s):
Start Date:
End Date:
Measureable Outcome:
Actual Outcome:
Current Status: